## Project Planner
Department of Health Building
55 North Willow Street
Planned Duration
[5 empty] | 2019 | [11 empty] | 2020
MAJOR ACTIVITY | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Contract Awards | bar: J to F
Breaking Ground | bar: M
Footings and Foundation | bar: A to 2019 J
Structural Steel | bar: 2019 J to 2019 S
Concrete Decks | bar: 2019 O to 2019 N
Exterior Walls | bar: 2019 N to 2019 J
Electrical Wiring | bar: 2019 N to 2020 S
Rooftop Equipment | bar: 2019 D
HVAC Main Ductwork | bar: 2019 D
Fireproofing | bar: 2019 D to 2019 J
Roof & Windows | bar: 2019 D to 2019 F
HVAC Distribution Ductwork | bar: 2019 J to 2019 M
Framing | bar: 2019 J to 2019 A
Ceiling and Walls | bar: 2019 F to 2020 J
Interior Finishes | bar: 2020 J to 2020 A
Furniture and Fixtures | bar: 2020 J to 2020 S
Target Occupancy Date | bar: 2020 O