## Sheet1
Phase (*add additional rows below as needed) | Anticipated Start Date | Anticipated Completion Date | Duration (in days) | Description
Planning Tasks | 2025-07-01 | 2026-02-15 | 229
Example: Finalize construction drawings | 2025-08-01 | 2026-01-31 | 183 | Develop and finalize retrofit project blueprints with architect
Key project milestone #1 |  |  | 0
Key project milestone #2 |  |  | 0
Key project milestone #3 |  |  | 0
Key project milestone #4 |  |  | 0
Key project milestone #5 |  |  | 0
Pre-Construction Tasks | 2026-02-16 | 2026-07-31 | 165
Example: Acquire permits | 2026-03-01 | 2026-06-30 | 121 | Acquire municipal permits for electrical and plumbing work for ground source heat pump
NJEDA site visit |  |  | 0 | Facilitate NJEDA site visit of project location(s) prior to construction initiation
Key project milestone #1 |  |  | 0
Key project milestone #2 |  |  | 0
Key project milestone #3 |  |  | 0
Key project milestone #4 |  |  | 0
Key project milestone #5 |  |  | 0
Tasks to Achieve One-Third Construction Progress | 2026-08-01 | 2027-01-31 | 183
Example: Site preparation | 2026-08-01 | 2026-08-15 | 14 | Setup construction trailer, fencing, cleanout pads, and equipment
Key project milestone #1 |  |  | 0
Key project milestone #2 |  |  | 0
Key project milestone #3 |  |  | 0
Key project milestone #4 |  |  | 0
Key project milestone #5 |  |  | 0
Tasks to Achieve Two-Thirds Construction Progress | 2027-02-01 | 2027-08-15 | 195
Example: Install solar panels | 2027-02-01 | 2027-02-14 | 13 | Install fifty 350-watt solar panels on building rooftop
Key project milestone #1 |  |  | 0
Key project milestone #2 |  |  | 0
Key project milestone #3 |  |  | 0
Key project milestone #4 |  |  | 0
Key project milestone #5 |  |  | 0
Tasks to Achieve Construction Completion | 2027-08-16 | 2028-02-15 | 183
Example: Complete final municipal inspection | 2027-02-01 | 2027-02-14 | 13 | Complete electrical and plumbing inspection closeout
Key project milestone #1 |  |  | 0
Key project milestone #2 |  |  | 0
Key project milestone #3 |  |  | 0
Key project milestone #4 |  |  | 0
Key project milestone #5 |  |  | 0
Post-Construction Tasks | 2028-02-16 | 2029-02-16
NJEDA site visit |  |  | 0 | Facilitate NJEDA site visit to project site after construction completion
Energy Data Reporting | 2028-02-16 | 2029-02-15 | 365 | Provide NJEDA with utility bills, energy consumption data, and building occupancy info one year after construction completion